## Sheet1
slno | Requirement | Status | Target Date | Completed Date
1 | 1. Menu for Stock count (all payment, pdc, spdc & mandate) | Completed | 2023-05-09 | 2023-05-09
2 | 2. Option to update Mandate pullout & VMS entry for Mandate if required. | Completed | 2023-05-08 | 2023-05-06
3 | 3. Bulk Mandate pullout update option | Completed | 2023-05-08 | 2023-05-08
4 | 4. Cheque level bulk pullout marking facility with various reason (Presented, Sent to chola with D.c. No. etc..) | Completed | 2023-05-08 | 2023-05-08
5 | 5. Cheque Level bulk Pullout removal – Entered as presented but not presented cases – avlble in Pre-conversion but not available in Post conversion cases / stop presented | Completed | 2023-05-10 | 2023-05-10
6 | 6. Error report – Finnone vs VMS – cheque level mismatch cases – Paymode, cheq no., amount, date etc…(old cases also) | Yet To start | 2023-05-12 | _
7 | 7. Bulk Status – option to have details for files received from TCS which will reduce time by avoiding already sent / pullout cases | Inprogress | 2023-05-11 | 2023-05-11